## Time_table
Working Weeks | 1 | Delay Week | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Start of the week | 2024-11-18 |  | 2024-11-25 | 2024-12-02 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-30 | 2025-01-06 | 2025-01-13 | 2025-01-20 | 2025-01-27 | 2025-02-03 | 2025-02-10 | 2025-02-17 | 2025-02-24 | 2025-03-03 | 2025-03-10 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-04-28 | 2025-05-05
Sensing and input working package | Documentation on the given guides and projects. Chose main languages and technologies. Create/adapt project plan. Members tasks asignation. | Jira set-up for task allocation | 2024-11-25: Camera handling, preprocessing, and getting rough output from the input devices/sensors.; 2025-01-13: Define other necessary sensors, define use-case, integration (IMU, distance), preprocessing, noise cancelling.; 2025-05-05: BFMC
Define use-case and test given servers information (localisation on map, cars interaction, gps interaction)
[19 empty] | Induce noise on all sensors and systems |  |  |  | Other functionalities and optimizations
Perception and scene understanding working package |  |  | 2024-11-25: Rough track set-up; 2024-12-16: Lane detection; 2024-12-30: Intersection detection; 2025-01-20: Traffic sign detection; 2025-02-17: Traffic light detection
[13 empty] | Position fusion | [5 empty] | Traffic lights detection & classification
[15 empty] | Define objects properties file |  |  |  | Object detection & classification
Environmental server interaction
Other functionalities and optimizations
Behaviour and motion plan working package |  |  | 2024-11-25: Define project architecture and communication between packages; 2025-01-20: Define path planning and validation; 2025-02-17: Define robustness and safety measures
Define decision making --> priorities of actions and state flow
[19 empty] | Induce noise on systems to valdiate robustness (loss of image, burned image, road search, undefined objects and states) |  |  |  | Other functionalities and optimizations
Vehicle control working packages |  |  | 2024-11-25: Lane following and speed control; 2025-01-20: Intersection navigation; 2025-02-17: Simpla action taking maneuvers (parking, stop for traffic sign, stop for traffic light, stop for pedestrian); 2025-03-17: Complex action taking maneuvers (swith lane for static and mobile car, road search)
Other functionalities and optimizations
Final result & Demo | Team can control the virtual car on the simulator. | Team can control the physical car via the frontend provided. | 2024-12-09: Robot can keep a lane, can make a curve; 2025-01-20: Robot can navigate in intersection; 2025-02-17: Robot can go on a pre-determined path, stop at stop sign, park at parking sign, slow at crosswalk; 2025-03-17: While detecting and calculating it's position, the robot can dynamicaly go to specified checkpoint, react to traffic lights, interact with other cars and send environemt data)
|  |  | Team defines and creates it's own phisical testing environment |  |  |  | Team defines a way of parallel developing and testing
Team installs the virtual testing environment
Other functionalities and optimizations
Deadlines |  |  | 2024-12-09: 2024-12-15; 2025-01-13: 2025-01-19; 2025-02-10: 2025-02-16; 2025-03-10: 2025-03-16; 2025-04-07: 2025-04-13; 2025-05-05: 2025-05-11
Checkpoint |  |  | 2024-12-09: 1st report; 2024-12-16: Christmas; 2025-01-13: 2nd report; 2025-02-10: 3rd report; 2025-03-10: Mid-term quality gate; 2025-04-07: 4th report; 2025-05-05: Finals